## Contents
Contents Table
Contents | Link
Annexure 1 - Estimated cost of the project | Ann 1'!A1
Annexure 2 - Means of Finance | Ann 2'!A1
Annexure 3 - Complete Estimate of Civil and Plant and Machinery | Ann 3'!A1
Annexure 4 - Estimated Cost of Production | Ann 4'!A1
Annexure 5- Projected balance sheet | Ann 5'!A1
Annexure 8 - Details of Manpower | Ann 8'!A1
Annexure 9 - Computation of Depreciation | Ann 9'!A1
Annexure 10 - Calculation of Income tax | Ann 10'!A1
Annexure 11- Break even analysis (At maximum capacity utilization) | Ann 11'!A1
Annexure 13 - Repayment schedule | Ann 13'!A1
Annexure 14 - Cash flow statement | Ann 14'!A1
Assumptions | Assumptions!A1
Sales Budget | Budgets!A1

## Ann 1
DPR with subsidy
Annexure 1 - Estimated cost of the project
Estimated cost of project
Sr. No. | Particulars | Grand Total (in lakhs)
1 | Land and site development
(a) | Land (Lease in name of company) | 0
| Total | 0
2 | Site Development | 16
(a) | Total | 16
3 | Civil Work
(a) | Civil Work | 0
| Total | 0
4 | Plant and Machinery (indegenous)
(a) | Plant and Machinery | 46
| Total | 46
5 | Miscellanoeus Fixed Assets
(a) | Cost | 0
6 | Working Capital Margin | 20
7 | Preliminary Expenses
(a) | Security Deposit | 0
Total
8 | Pre-Operative Expense
(for 6 months upto the date od commencement of commercial production)
(a) | Establisment and Travelling and Other Expenses | 0
(b) | Legal and Misc Expense | 0
| Total | 0
9 | E mandi expense | 0
| Total Cost of Project | 82

## Ann 2
Annexure 2 - Means of Finance
Sr. No. | Item | Grand Total (in lakhs)
1 | Promoter's equity | 8.2
2 | Eligible Assistance | 0
3 | Term Loan | 53.8
4 | CC Limit | 20
| Total | 82

## Ann 3
Annexure 3 - Complete Estimate of Civil and Plant and Machinery
1. Building |  | Units |  | Amt
1 | Building as per estimate | 1 |  | 1600000
Total Plant and Machinery |  |  |  | 1600000
2. Plant and machinery |  | Units | Capacity | Amt
1 | Automatic Oil expeller | 2 |  | 1000000
2 | Motor | 2 |  | 400000
3 | Oil filter |  |  | 50000
4 | Boilers | 2 |  | 80000
5 | Oil storage tank | 3 |  | 60000
6 | Shaker with blower | 1 |  | 30000
7 | Weighing scale | 1 |  | 50000
8 | Packaging machine |  |  | 200000
9 | Tractor (for foraying the produce to and from farm) |  |  | 500000
10 | Electrical expense including generator |  |  | 1200000
11 | Bucket elevator | 2 |  | 300000
12 | seed cleaner |  |  | 200000
13 | Conveyor belt | 1 |  | 200000
14 | Oil testing equipment |  |  | 250000
15 | Miscellaneous |  |  | 80000
Total Plant and Machinery |  |  |  | 4600000
Total fixed Assets |  |  |  | 6200000

## Ann 4
Annexure 4 - Estimated Cost of Production
Sr. No | Description | Year ending March 31st
|  | I | II | III | IV | V | VI | VII | VIII | IX
| No of Working months | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Purchase of raw material input | 227500000 | 255937500 | 273000000 | 290062500 | 307125000 | 324187500 | 341250000 | 341250000 | 341250000
| Electricity expense | 11800000 | 12340000 | 12907000 | 13502350 | 14127467.5 | 14783840.875 | 15473032.9188 | 15473032.9188 | 15473032.9188
| Running and Manintenance expense @15% of procurement cost | 34125000 | 38390625 | 40950000 | 43509375 | 46068750 | 48628125 | 51187500 | 51187500 | 51187500
| Fixed running cost | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000
| Cost of Production | 274625000 | 307868125 | 328057000 | 348274225 | 368521217.5 | 388799465.875 | 409110532.9187 | 409110532.9187 | 409110532.9187
| Add: Opening stock | 0 | 2630250 | 5448375 | 8454375 | 11648250 | 8266500 | 4696875 | 939375 | 0
| Less: Closing stock | 2630250 | 5448375 | 8454375 | 11648250 | 8266500 | 4696875 | 939375 | 0 | 0
| Sub Total | 271994750 | 305050000 | 325051000 | 345080350 | 371902967.5 | 392369090.875 | 412868032.9187 | 410049907.9187 | 409110532.9187
| Administrative salaries and wages | 1696320 | 1798099.2 | 1905985.152 | 2020344.2611 | 2141564.9168 | 2270058.8118 | 2406262.3405 | 2550638.0809 | 2703676.3658
| Packaging cost @ Rs. 2 per kg | 6300000 | 6750000 | 7200000 | 7650000 | 8100000 | 8550000 | 9000000 | 9000000 | 9000000
| Selling expenses @ Rs. 2.5 per kg | 7796250 | 8353125 | 8910000 | 9466875 | 10226250 | 10794375 | 11362500 | 11278125 | 11250000
| Total | 15792570 | 16901224.2 | 18015985.152 | 19137219.2611 | 20467814.9168 | 21614433.8118 | 22768762.3405 | 22828763.0809 | 22953676.3658
| Cost of Sales | 287787320 | 321951224.2 | 343066985.152 | 364217569.2611 | 392370782.4168 | 413983524.6868 | 435636795.2593 | 432878670.9997 | 432064209.2845
| Expected sales revenue | 289327500 | 325493437.5 | 347193000 | 368892562.5 | 398482875 | 420620812.5 | 442758750 | 439470937.5 | 438375000
| Gross Profit | 1540180 | 3542213.3 | 4126014.848 | 4674993.2389 | 6112092.5832 | 6637287.8132 | 7121954.7407 | 6592266.5003 | 6310790.7155
Financial expense
| Interest on Term Loan | 319696.1538 | 279346.1538 | 229684.6154 | 180023.0769 | 130361.5385 | 46557.6923 | 0 | 0 | 0
| Interest on WC Loan | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
| total | 519696.1538 | 479346.1538 | 429684.6154 | 380023.0769 | 330361.5385 | 246557.6923 | 200000 | 200000 | 200000
| Operating profits (PBT) | 1020483.8462 | 3062867.1462 | 3696330.2326 | 4294970.162 | 5781731.0448 | 6390730.1209 | 6921954.7407 | 6392266.5003 | 6110790.7155
| Preliminary Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| depreciation | 850000 | 730500 | 628125 | 540386.25 | 465160.3125 | 400635.0656 | 345263.7258 | 297725.6949 | 256893.2159
| Other income - Subsidy for repayment of loan | 0 | 0 | 0 | 0 | 0 | 1250000 | 0 | 0 | 0
| Net Profit before Tax | 170483.8462 | 2332367.1462 | 3068205.2326 | 3754583.912 | 5316570.7323 | 7240095.0553 | 6576691.015 | 6094540.8054 | 5853897.4996
| Income Tax | 51145.1538 | 699710.1438 | 920461.5698 | 1126375.1736 | 1594971.2197 | 1797028.5166 | 1973007.3045 | 1828362.2416 | 1756169.2499
| Profits after Tax | 119338.6923 | 1632657.0023 | 2147743.6628 | 2628208.7384 | 3721599.5126 | 5443066.5387 | 4603683.7105 | 4266178.5638 | 4097728.2497
| Distribution of profits (50%) | 59669.3462 | 816328.5012 | 1073871.8314 | 1314104.3692 | 1860799.7563 | 2721533.2693 | 2301841.8552 | 2133089.2819 | 2048864.1249
| Profit transfer to balance sheet | 59669.3462 | 816328.5012 | 1073871.8314 | 1314104.3692 | 1860799.7563 | 2721533.2693 | 2301841.8552 | 2133089.2819 | 2048864.1249
1. Electricity are semi-fixed cost. Rs. 10,00,000 pa is fixed, balance is variable at Rs. 12 per unit usage
2. Electricity usage in units is given below
| Usage in units | 900000 | 945000 | 992250 | 1041862.5 | 1093955.625 | 1148653.4062 | 1206086.0766 | 1206086.0766 | 1206086.0766
| Variable cost | 10800000 | 11340000 | 11907000 | 12502350 | 13127467.5 | 13783840.875 | 14473032.9188 | 14473032.9188 | 14473032.9188
3. Closing stock is valued at Rs. 120 per kg

## Ann 5
Annexure 5- Projected balance sheet
Projected Balance sheet
Sr. No | Description | Year ending March 31st
|  | I | II | III | IV | V | VI | VII | VIII | IX
A | Asset
1 | Fixed Capital expenditure
| Gross Block | 6200000 | 5350000 | 4619500 | 3991375 | 3450988.75 | 2985828.4375 | 2585193.3719 | 2239929.6461 | 1942203.9512
| Less- Depreciation | 850000 | 730500 | 628125 | 540386.25 | 465160.3125 | 400635.0656 | 345263.7258 | 297725.6949 | 256893.2159
| net Block | 5350000 | 4619500 | 3991375 | 3450988.75 | 2985828.4375 | 2585193.3719 | 2239929.6461 | 1942203.9512 | 1685310.7353
2 | Closing Stock | 2630250 | 5448375 | 8454375 | 11648250 | 8266500 | 4696875 | 939375 | 0 | 0
3 | Sundry debtors | 28932750 | 27124453.125 | 28932750 | 30741046.875 | 33206906.25 | 35051734.375 | 36896562.5 | 36622578.125 | 36531250
4 | Cash/ bank balance | 16432823.1923 | 13298381.2608 | 12202138.9095 | 11070515.346 | 16328423.7321 | 22363754.3267 | 29767281.7827 | 33411456.1345 | 35808541.6002
| Total assets | 53345823.1923 | 50490709.3858 | 53580638.9095 | 56910800.971 | 60787658.4196 | 64697557.0735 | 69843148.9288 | 71976238.2107 | 74025102.3355
B | Liabilities
1 | Capital | 820000 | 879669.3462 | 1695997.8473 | 2769869.6787 | 4083974.0479 | 5944773.8042 | 8666307.0735 | 10968148.9288 | 13101238.2107
| Add- Profit | 59669.3462 | 816328.5012 | 1073871.8314 | 1314104.3692 | 1860799.7563 | 2721533.2693 | 2301841.8552 | 2133089.2819 | 2048864.1249
| Less- Drawings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Closing capital | 879669.3462 | 1695997.8473 | 2769869.6787 | 4083974.0479 | 5944773.8042 | 8666307.0735 | 10968148.9288 | 13101238.2107 | 15150102.3355
2 | term Loan | 4966153.8462 | 4138461.5385 | 3310769.2308 | 2483076.9231 | 1655384.6154 | 0 | 0 | 0 | 0
3 | Working capital | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
4 | Creditors | 45500000 | 42656250 | 45500000 | 48343750 | 51187500 | 54031250 | 56875000 | 56875000 | 56875000
| Total liabilities | 53345823.1923 | 50490709.3858 | 53580638.9095 | 56910800.971 | 60787658.4196 | 64697557.0735 | 69843148.9288 | 71976238.2107 | 74025102.3355
Current Ratio
| Current Assets | 45365573.1923 | 40422834.3858 | 41134888.9095 | 41811562.221 | 49535329.9821 | 57415488.7017 | 66663844.2827 | 70034034.2595 | 72339791.6002
| Current Liabilities | 45500000 | 42656250 | 45500000 | 48343750 | 51187500 | 54031250 | 56875000 | 56875000 | 56875000
| Ratio | 0.99705 | 0.94764 | 0.90406 | 0.86488 | 0.96772 | 1.0626 | 1.1721 | 1.2314 | 1.2719
| Average |  |  |  | 1.0466
Debt Equity ratio
| Debt | 6966153.8462 | 6138461.5385 | 5310769.2308 | 4483076.9231 | 3655384.6154 | 2000000 | 2000000 | 2000000 | 2000000
| Equity | 879669.3462 | 1695997.8473 | 2769869.6787 | 4083974.0479 | 5944773.8042 | 8666307.0735 | 10968148.9288 | 13101238.2107 | 15150102.3355
| Ratio | 7.9191 | 3.6194 | 1.9173 | 1.0977 | 0.61489 | 0.23078 | 0.18235 | 0.15266 | 0.13201
| Average |  |  |  | 1.7629
Fixed asset coverage ratio
| Fixed assets | 5350000 | 4619500 | 3991375 | 3450988.75 | 2985828.4375 | 2585193.3719 | 2239929.6461 | 1942203.9512 | 1685310.7353
| Debt | 6966153.8462 | 6138461.5385 | 5310769.2308 | 4483076.9231 | 3655384.6154 | 2000000 | 2000000 | 2000000 | 2000000
| ratio | 0.768 | 0.75255 | 0.75156 | 0.76978 | 0.81683 | 1.2926 | 0 | 0 | 0
0.57237
Debt service coverage ratio
| Interest on loan (TL + WC) | 519696.1538 | 479346.1538 | 429684.6154 | 380023.0769 | 330361.5385 | 246557.6923 | 200000 | 200000 | 200000
| Instalment of loan | 2413846.1538 | 2827692.3077 | 2827692.3077 | 2827692.3077 | 2827692.3077 | 2405384.6154 | 2000000 | 2000000 | 2000000
| Total | 2933542.3077 | 3307038.4615 | 3257376.9231 | 3207715.3846 | 3158053.8462 | 2651942.3077 | 2200000 | 2200000 | 2200000
| Net operating income | 1540180 | 3542213.3 | 4126014.848 | 4674993.2389 | 6112092.5832 | 6637287.8132 | 7121954.7407 | 6592266.5003 | 6310790.7155
| ratio | 0.52502 | 1.0711 | 1.2667 | 1.4574 | 1.9354 | 2.5028 | 3.2373 | 0 | 0
| Average |  |  |  | 1.2511
1. asssumed that 60 days of purchases are average creditors maintained
2. assumed that 30 days of sales are average debtors maintained by the business

## Ann 8
Annexure 8 - Details of Manpower
Details of Manpower
S. No. | Designation | In no. | Salary per person per month | Annual cost
i. | Machine operators | 2 | 17000 | 408000
ii. | Accountant | 1 | 29000 | 348000
iii. | Labour/ helper | 3 | 12000 | 432000
iv. | Security | 2 | 9400 | 225600
Total |  |  |  | 1413600
Add: benefits @ 20% |  |  |  | 282720
Total |  |  |  | 1696320
Total annual wages |  |  |  | 1696320
Annual increase in wages |  |  |  | 6%
Total manpower |  |  |  | 8

## Ann 9
Annexure 9 - Computation of Depreciation
Computation of Depreciation
Sr. No. | Particulars | Building and civil work | Plant and Machinery | Misc Fixed Asset | Amount in lakhs
i. | Cost | 1600000 | 4600000 | 0 | 62
ii. | Pre operatives | 0 | 0 | 0 | 0
iii. | Contingencies | 0 | 0 | 0 | 0
| Total |  |  |  | 62
| Rates of Depreciation | 10% | 15% | 10% | Total depreciation for the year
Year | 1 | 160000 | 690000 | 0 | 850000
Year | 2 | 144000 | 586500 | 0 | 730500
Year | 3 | 129600 | 498525 | 0 | 628125
Year | 4 | 116640 | 423746.25 | 0 | 540386.25
Year | 5 | 104976 | 360184.3125 | 0 | 465160.3125
Year | 6 | 94478.4 | 306156.6656 | 0 | 400635.0656
Year | 7 | 85030.56 | 260233.1658 | 0 | 345263.7258
Year | 8 | 76527.504 | 221198.1909 | 0 | 297725.6949
Year | 9 | 68874.7536 | 188018.4623 | 0 | 256893.2159

## Ann 10
Annexure 10 - Calculation of Income tax
Calculation of Income Tax
Particulars | Year ending March 31st
| I | II | III | IV | V | VI | VII | VIII | IX
Net profit before tax | 1020483.8462 | 3062867.1462 | 3696330.2326 | 4294970.162 | 5781731.0448 | 6390730.1209 | 6921954.7407 | 6392266.5003 | 6110790.7155
Add- dep on SLM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub total | 1020483.8462 | 3062867.1462 | 3696330.2326 | 4294970.162 | 5781731.0448 | 6390730.1209 | 6921954.7407 | 6392266.5003 | 6110790.7155
Less- Dep on WDV | 850000 | 730500 | 628125 | 540386.25 | 465160.3125 | 400635.0656 | 345263.7258 | 297725.6949 | 256893.2159
Sub total | 170483.8462 | 2332367.1462 | 3068205.2326 | 3754583.912 | 5316570.7323 | 5990095.0553 | 6576691.015 | 6094540.8054 | 5853897.4996
Less - Deductions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Taxable profits | 170483.8462 | 2332367.1462 | 3068205.2326 | 3754583.912 | 5316570.7323 | 5990095.0553 | 6576691.015 | 6094540.8054 | 5853897.4996
Income tax @30% | 51145.1538 | 699710.1438 | 920461.5698 | 1126375.1736 | 1594971.2197 | 1797028.5166 | 1973007.3045 | 1828362.2416 | 1756169.2499

## Ann 11
Annexure 11- Break even analysis (At maximum capacity utilization)
Break even capacity at maximum capacity utilixzation
| Sales |  |  | 413325000
Variable cost
| - Procurement cost of inputs |  | 325000000
| - Running and maintenance cost |  | 4875000
| - Interest on Working capital |  | 200000
| - electricity expense |  | 1456086.0766 | 331531086.0766
| Contribution |  |  | 81793913.9234
Less: fixed cost
| Wages and salaries |  |  | 1696320
| Depreciation |  |  | 850000
| Electricity |  |  | 1000000
| Fixed running expense |  |  | 1200000
| Interest on TL |  |  | 319696.1538
| Fixed cost |  |  | 5066016.1538
| Particulars | Oil | Cake
| Sales price per kg | 160 | 39
| Procurement cost of rapeseed | 36.1111 | 26
| Running and maintenance cost | 3.6111 | 3.9
| Interest on Working capital | 0.04 | 0.04
| selling expenses | 2.5 | 2.5
| Packaging cost | 2 | 2
| Electricity charges | 0.29122 | 0.29122
| Contribution per kg | 115.4466 | 4.2688
| Contribution margin | 72.15% | 10.95%
| Sales mix | 44.44% | 55.56%
| Proportionate contribution | 32.07% | 6.081% | 38.15%
| BEP total in Rs. | 13279420.6828
| BEP | 32.13%
Break-even point is the condition when an entity generate sufficient revenue that it can meet its fixed expense after deducting any variable expense, i.e., the point where contribution is equal to the fixed expense.
For the first year of operation the break-even capacity comes at 32.13% capacity, it is because of the fact that in the Initial year the fixed expense of consultancy for project is taken in to consideration for calculation of BEP. considering our operational capacity in year 1 to be 75% which is more than the BEP, hence we can conclude that the project is sound enough to cover its fixed expense.

## Ann 12 (hidden)
Annexure 12 - Profitability statement
Years
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Vegetable procument expense | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Fruits procurement expense | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Direct Expenses

## Ann 13
Annexure 13 - Repayment schedule
Repayment schedule
Amount of Loan (in lakhs) |  |  | 53.8
Amount of subsidy (in lakhs) |  |  | 12.5
Rate of interest |  |  | 6%
Moratorium period |  |  | 6 months
Year | Quarter | Balance outstanding | Principal instalment | Interest
1 | 1 | 53.8 | 0 | 0.807
| 2 | 53.8 | 0 | 0.807
| 3 | 53.8 | 2.0692 | 0.807
| 4 | 51.7308 | 2.0692 | 0.77596
2 | 1 | 49.6615 | 2.0692 | 0.74492
| 2 | 47.5923 | 2.0692 | 0.71388
| 3 | 45.5231 | 2.0692 | 0.68285
| 4 | 43.4538 | 2.0692 | 0.65181
3 | 1 | 41.3846 | 2.0692 | 0.62077
| 2 | 39.3154 | 2.0692 | 0.58973
| 3 | 37.2462 | 2.0692 | 0.55869
| 4 | 35.1769 | 2.0692 | 0.52765
4 | 1 | 33.1077 | 2.0692 | 0.49662
| 2 | 31.0385 | 2.0692 | 0.46558
| 3 | 28.9692 | 2.0692 | 0.43454
| 4 | 26.9 | 2.0692 | 0.4035
5 | 1 | 24.8308 | 2.0692 | 0.37246
| 2 | 22.7615 | 2.0692 | 0.34142
| 3 | 20.6923 | 2.0692 | 0.31038
| 4 | 18.6231 | 2.0692 | 0.27935
6 | 1 | 16.5538 | 2.0692 | 0.24831
| 2 | 14.4846 | 1.9846 | 0.21727
| 3 | 12.5 | 0 | 0
| 4 | 0 | 0 | 0
7 | 1 | 0 | 0 | 0
| 2 | 0 | 0 | 0
| 3 | 0 | 0 | 0
| 4 | 0 | 0 | 0

## Ann 14
Annexure 14 - Cash flow statement
Particulars | 0 | I | II | III | IV | V | VI | VII | VIII | IX
opening balance | 2000000 | 2000000 | 16432823.1923 | 13298381.2608 | 12202138.9095 | 11070515.346 | 16328423.7321 | 22363754.3267 | 29767281.7827 | 33411456.1345
Add: Capital | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add: Loan disbursement | 5380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Less: Purchase of asset | 6200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add: Sales realizations | 0 | 260394750 | 298368984.375 | 318260250 | 338151515.625 | 365275968.75 | 385569078.125 | 405862187.5 | 402848359.375 | 401843750
Less: Payment made to creditors of previos year | 0 | 0 | 45500000 | 42656250 | 45500000 | 48343750 | 51187500 | 54031250 | 56875000 | 56875000
Add: Receipts from debtors of previos year | 0 | 0 | 28932750 | 27124453.125 | 28932750 | 30741046.875 | 33206906.25 | 35051734.375 | 36896562.5 | 36622578.125
Less: Payments made for current year purchase | 0 | 244917570 | 282113099.2 | 300572985.152 | 319067694.2611 | 337801532.4168 | 356382649.6868 | 375004295.2593 | 375064295.9997 | 375189209.2845
Less: Interest payments | 0 | 519696.1538 | 479346.1538 | 429684.6154 | 380023.0769 | 330361.5385 | 246557.6923 | 200000 | 200000 | 200000
| 0 | 16957483.8462 | 15642112.2135 | 15024164.6184 | 14338687.1964 | 20611887.0157 | 27287700.728 | 34042130.9424 | 37372907.658 | 39613574.975
Less: Income tax | 0 | 51145.1538 | 699710.1438 | 920461.5698 | 1126375.1736 | 1594971.2197 | 1797028.5166 | 1973007.3045 | 1828362.2416 | 1756169.2499
| 0 | 16906338.6923 | 14942402.0696 | 14103703.0486 | 13212312.0229 | 19016915.7961 | 25490672.2114 | 32069123.6379 | 35544545.4164 | 37857405.7251
Less: Distrubutions made from profits | 0 | 59669.3462 | 816328.5012 | 1073871.8314 | 1314104.3692 | 1860799.7563 | 2721533.2693 | 2301841.8552 | 2133089.2819 | 2048864.1249
| 0 | 16846669.3462 | 14126073.5685 | 13029831.2172 | 11898207.6537 | 17156116.0398 | 22769138.9421 | 29767281.7827 | 33411456.1345 | 35808541.6002
Less: Principal repayment of loan | 0 | 413846.1538 | 827692.3077 | 827692.3077 | 827692.3077 | 827692.3077 | 405384.6154 | 0 | 0 | 0
Closing cash balance | 2000000 | 16432823.1923 | 13298381.2608 | 12202138.9095 | 11070515.346 | 16328423.7321 | 22363754.3267 | 29767281.7827 | 33411456.1345 | 35808541.6002
PV dicounting rate | 6%
PVF | 1 | 0.9434 | 0.89 | 0.83962 | 0.79209 | 0.74726 | 0.70496 | 0.66506 | 0.62741 | 0.5919
Inflows | 8200000 | 262394750 | 343734557.5673 | 358683084.3858 | 379286404.5345 | 407087530.971 | 435104408.1071 | 463277676.2017 | 469512203.6577 | 471877784.2595
PV of Inflows | 8200000 | 247542216.9811 | 305922532.5448 | 301157234.1478 | 300430357.5841 | 304199484.5899 | 306731438.6869 | 308106114.1403 | 294577765.0708 | 279303735.4771
Outflows | 6200000 | 245961926.8077 | 330436176.3065 | 346480945.4763 | 368215889.1885 | 390759107.2389 | 412740653.7804 | 433510394.419 | 436100747.5232 | 436069242.6593
PV of Outflows | 6200000 | 232039553.5922 | 294087020.5647 | 290912083.0251 | 291661472.5298 | 291997936.5061 | 290965874.3505 | 288309171.6376 | 273615004.1475 | 258108714.7227
Net cash inflow | 2000000 | 16432823.1923 | 13298381.2608 | 12202138.9095 | 11070515.346 | 16328423.7321 | 22363754.3267 | 29767281.7827 | 33411456.1345 | 35808541.6002
Net Present value | 2000000 | 15502663.389 | 11835511.98 | 10245151.1226 | 8768885.0543 | 12201548.0838 | 15765564.3364 | 19796942.5028 | 20962760.9233 | 21195020.7544 | 138274048.1467

## Budgets
Sales Budget
Particulars | Year ending March 31st
| I | II | III | IV | V | VI | VII | VIII | IX
Production capacity utilization | 70% | 75% | 80% | 85% | 90% | 95% | 100% | 100% | 100%
Production qty for oil | 1400000 | 1500000 | 1600000 | 1700000 | 1800000 | 1900000 | 2000000 | 2000000 | 2000000
Production qty for cake | 1750000 | 1875000 | 2000000 | 2125000 | 2250000 | 2375000 | 2500000 | 2500000 | 2500000
Sale qty for oil | 1386000 | 1485000 | 1584000 | 1683000 | 1818000 | 1919000 | 2020000 | 2005000 | 2000000
Sale qty for cake | 1732500 | 1856250 | 1980000 | 2103750 | 2272500 | 2398750 | 2525000 | 2506250 | 2500000
Sales for Oil | 221760000 | 249480000 | 266112000 | 282744000 | 305424000 | 322392000 | 339360000 | 336840000 | 336000000
Sales for Cake | 67567500 | 76013437.5 | 81081000 | 86148562.5 | 93058875 | 98228812.5 | 103398750 | 102630937.5 | 102375000
Total Sales | 289327500 | 325493437.5 | 347193000 | 368892562.5 | 398482875 | 420620812.5 | 442758750 | 439470937.5 | 438375000
Production budget
Production capacity | 70%: 20000; 75%: kg per day
Production days in a year | 70%: 250; 75%: days
Production qty in a year | 70%: 5000000; 75%: kgs
Products | 70%: Production at 100% capacity; 75%: sales prices for oil per kg in year I; 80%: purchase prices per kg in year I; 85%: sales prices for cake per kg in year I
Output | 70%: 5000000; 75%: 160; 80%: 65; 85%: 39
Output stock calculation - For oil
Particulars | 70%: Year ending March 31st
| I | II | III | IV | V | VI | VII | VIII | IX
Opening Stock | 0 | 14000 | 29000 | 45000 | 62000 | 44000 | 25000 | 5000 | 0
Add: Production | 1400000 | 1500000 | 1600000 | 1700000 | 1800000 | 1900000 | 2000000 | 2000000 | 2000000
Ouput available for sale | 1400000 | 1514000 | 1629000 | 1745000 | 1862000 | 1944000 | 2025000 | 2005000 | 2000000
Less: Sales | 1386000 | 1485000 | 1584000 | 1683000 | 1818000 | 1919000 | 2020000 | 2005000 | 2000000
Closing Stock | 14000 | 29000 | 45000 | 62000 | 44000 | 25000 | 5000 | 0 | 0
Value for closing stock | 2016000 | 4176000 | 6480000 | 8928000 | 6336000 | 3600000 | 720000 | 0 | 0
Particulars | 70%: Year ending March 31st
| I | II | III | IV | V | VI | VII | VIII | IX
Opening Stock | 0 | 17500 | 36250 | 56250 | 77500 | 55000 | 31250 | 6250 | 0
Add: Production | 1750000 | 1875000 | 2000000 | 2125000 | 2250000 | 2375000 | 2500000 | 2500000 | 2500000
Ouput available for sale | 1750000 | 1892500 | 2036250 | 2181250 | 2327500 | 2430000 | 2531250 | 2506250 | 2500000
Less: Sales | 1732500 | 1856250 | 1980000 | 2103750 | 2272500 | 2398750 | 2525000 | 2506250 | 2500000
Closing Stock | 17500 | 36250 | 56250 | 77500 | 55000 | 31250 | 6250 | 0 | 0
Value for closing stock | 614250 | 1272375 | 1974375 | 2720250 | 1930500 | 1096875 | 219375 | 0 | 0
Assumptions:
1. assumed that 99% of production is sold for first 5 years, thereafter demand is almost 101% of output but we are able to serve market according to the availablility of output
input output ratio is 50%, i.e., 1 kg of rapeseed would produce 0.5 kg/ litre of oil
Proportion
Wastage | 70%: 10%
oil | 70%: 40%
Cake | 70%: 50%

## For word file (hidden)
| I | II | III | IV | V | VI | VII | VIII | IX
Turnover | 2893.275 | 3254.9344 | 3471.93 | 3688.9256 | 3984.8288 | 4206.2081 | 4427.5875 | 4394.7094 | 4383.75
Cost Of operations | 2877.8732 | 3219.5122 | 3430.6699 | 3642.1757 | 3923.7078 | 4139.8352 | 4356.368 | 4328.7867 | 4320.6421
Gross profit | 15.4018 | 35.4221 | 41.2601 | 46.7499 | 61.1209 | 66.3729 | 71.2195 | 65.9227 | 63.1079
EBITDA | 15.4018 | 35.4221 | 41.2601 | 46.7499 | 61.1209 | 66.3729 | 71.2195 | 65.9227 | 63.1079
Profit before tax | 1.7048 | 23.3237 | 30.6821 | 37.5458 | 53.1657 | 72.401 | 65.7669 | 60.9454 | 58.539
Profit after tax | 1.1934 | 16.3266 | 21.4774 | 26.2821 | 37.216 | 54.4307 | 46.0368 | 42.6618 | 40.9773

## Assumptions
S. no. | Assumptions
1 | Electricity are semi-fixed cost. Rs. 10,00,000 pa is fixed, balance is variable at Rs. 12 per unit usage
2 | Electricity usage in units is given below
|  | Usage in units | 900000 | 945000 | 992250 | 1041862.5 | 1093955.625 | 1148653.4062 | 1206086.0766 | 1206086.0766 | 1206086.0766
|  | Variable cost | 10800000 | 11340000 | 11907000 | 12502350 | 13127467.5 | 13783840.875 | 14473032.9188 | 14473032.9188 | 14473032.9188
3 | Closing stock is valued at Rs. 120 per kg
4 | Asssumed that 60 days of purchases are average creditors maintained
5 | Assumed that 30 days of sales are average debtors maintained by the business
6 | It is assumed that input output ratio of mustard oil production is 50%, i.e., to produce output of 1 litre of oil- 2 kg of rapeseed is required to be processed
7 | The selling expense per kg is takes to be variable @ Rs. 2.5 per kg of output sold
8 | Packing expense is variable at Rs 2 per kg
9 | There are some miscellaneous expenses assumed for managing office and employees expense. This is semi fixed cost, fixed to the extent of Rs 10 lakhs per annum and variable @ 1% of sales. The fixed expense would increase after 5 years by 20%

## Sheet1 (hidden)
cash flow statement
| I | II | III | IV | V | VI | VII | VIII | IX
Sales realized | 260394750 | 292944093.75 | 312473700 | 332003306.25 | 358634587.5 | 378558731.25 | 398482875 | 395523843.75 | 394537500
Term loan | 5000000
assisstance | 21492978
less- Purchase of assets | 6200000